## DOI
DOI |  | 10.5281/zenodo.1172052
Contributors | Zoltán | Lux | National Archives of Slovenia
| József | Mezei | National Archives of Slovenia
| István | Alföldi | National Archives of Hungary
| David | Anderson | University of Brighton
| Janet | Anderson | University of Brighton
Release Date: |  | 12th February 2012
Deliverable |  | D2.4.PD7
Version |  | 3.2

## Pilot Overview
Pilot 7 | Access to Databases
Task leader | National Archives of Hungary
Supported by | Danish National Archives
Scope | Representation of not less than 2 databases of different sizes and complexities with restricted and open content.
Object | Extract data from the EDRMS and the databases, create SIPs for structured and unstructured records using the ESSArch Tools, ingest the SIPs to the repository using the ESSArch Preservation Platform, for further evaluation
Short description | NAH will extract structured content from an Oracle database with the tools developed by WP3. The pilot will examine the applicability of data-warehouse concepts in an archival environment in order to maintain both the original structure and intellectual interpretability of ingested data. The working prototype for access will be a user-friendly web-based application based on the DIP specification of WP5
Timeframe | M25-M27: setting up the pilot sites; M28-M31: running the pilots; M32-M33: testing and reporting.
Preconditions | M03.3, M03.4, M04.2, M05.4, M05.6 (DoW)
Contacts | Name (Title) | [9 empty] | E-mail | [9 empty] | Skype
Contact Person | Zoltan Lux | [9 empty] | lux.zoltan@mnl.gov.hu | [9 empty] | lux.zoltan1
Pilot staff member | József Mezei | [9 empty] | mezei.jozsef@mnl.gov.hu | [9 empty] | jmezei_92
Pilot staff member
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
| X |  | X |  |  |  |  | X |  |  | X |  |  |  |  | X |  | X | X | X |  | X | [5 empty] | X
Pilot Scenarios
Scenario 1 | SIP Creation and Ingest of old (not normalized) database in SIARD 2.0 format
Scenario 2 | SIP Creation and Ingest of unstructured files
Scenario 3 | Extract SIARD Package from Preservica/E-ARK AIP (APEX/Oracle BI access)
Scenario 4 | Search and present SIARD based information with E-ARK access tools (HADOOP based search and access with HIVE Presentation in local environment)
Scenario 5 | Access information from unstructured files (Access PDF documents and image files with EAD metadata as Preservica/E-ARK DIP)
Success Criteria
General | The following E-ARK tools will be tested in a pilot environment: DBPTK, RODA-in and DB viewer (Sofia) using Oracle OLAP Viewer, along with components of the Integrated Protoype (E-ARK Web): SIP2AIP, HDFS-Storage, Lily-Igest, Search, AIP2DIP, with the integration of Oracle (OLAP Viwer). (Yes/No)
Scenario 1 | Create SIP and Ingest more then 300.000 cases of old (not normalized) database of the Hungarian Prosecution Office. (90% success rate)
Scenario 2 | Create SIP and Ingest more then 30.000 pages of scanned pdf images of meeting minutes of the former Hungarian Socialist Party. (95% success rate)
Scenario 3 | Provide access for more then 300.000 cases of old (not normalized) database of the Hungarian Prosecution Office. (90% success rate)
Scenario 4 | Provide access for more then 300.000 cases of old (not normalized) database of the Hungarian Prosecution Office. (90% success rate)
Scenario 5 | Provide access for more then 30.000 pages of scanned pdf images of meeting minutes of the former Hungarian Socialist Party. (95% success rate)

## Pilot Data
Pilot 3 | Pilot Data
Information Packages (IP) | IP |  | Note
| E-ARK SIP | x
| non E-ARK SIP | x | Preservica XIP
| E-ARK AIP | x
| non E-ARK AIP | x | Preservica AIP
| E-ARK DIP | x
| non E-ARK DIP | x | APEX, HIVE, Lily, Oracle Warehouse Builder
Pilot data description
Data Set 1 | Hungarian Prosecution Office database
Description | Old (not normalized) database in CSV exports of DBASE files.
Data type | CSV files
Metadata format | none
Quantity | more then 300.000 cases and 500.000 name. (1,6 GB)
Data Set 2 | Scanned meeting minutes of the Central Coimmettee of the Hungarian Socialist Party
Description | Scanned documents in file systems in PDF file and corresponding metadata (EAD)
Data type | PDF/JPG files (representations)
Metadata format | EAD
Quantity | 123.225 files. (101 GB)

## Pilot Scenarios
Pilot 7 | Scenarios
Scenario 1 | SIP Creation and Ingest of old (not normalized) database in SIARD 2.0 format
Description | Create SIP from old (not normalized) database B25. The data is in CSV exports of DBASE files. Create both E-ARK and local SIPs and ingest them into E-ARK Web HDFS storage and Preservica archival repository. Both E-ARK and local AIPs are generated during the ingest.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
| X |  | X |  |  |  |  | X |  |  | X
Use-case | Relational database based on SIARD 2.0
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 2 | SIP Creation and Ingest of unstructured files
Description | Create SIP from scanned documents of the Meeting minutes of the Central Coimmettee of the Hungarian Socialist Party. The image files are in PDF format with EAD metadata. Create both E-ARK and local SIPs and ingest them into B27and Preservica archival repository. Both E-ARK and local AIPs are generated during the ingest.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [5 empty] | X | E-ARK AIP |  |  | X | E-ARK DIP
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
|  |  | X |  |  |  |  | X |  |  | X
Use-case | Extract and Ingest computer files from simple file-system - Other (please specify)
Note | Scanned document images in PDF files
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 3 | Extract SIARD Package from Preservica/E-ARK AIP
Description | Access database infromation of the Hungarian Prosecution Office in SIARD format using APEX and OWB access. Both E-ARK and local DIPs are generated during access.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [6 empty] | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
[11 empty] | X |  |  |  |  | X |  | X | X | X
Use-case | Other (please specify content type and presentation tool)
Note | Access database via APEX and Oracle BI
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 4 | Search and present SIARD based information with E-ARK access tools
Description | Access database infromation of the Hungarian Prosecution Office in SIARD format using HADOOP based search and access with HIVE Lily Presentation in local environment.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [6 empty] | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
[11 empty] | X |  |  |  |  | X |  | X | X | X | [7 empty] | X
Use-case | Access data with OLAP via oracle
Note
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]
Scenario 5 | Access information from unstructured files
Description | Create DIP from scanned documents of the Meeting minutes of the Central Coimmettee of the Hungarian Socialist Party. The image files are in PDF format with EAD metadata in E-ARK Web HDFS storage and Preservica. Create both E-ARK and local DIPs.
OAIS Relevance E-ARK Tools | Pre-Ingest | [6 empty] | Ingest - Storage |  |  |  | Storage - Access
| E-ARK SIP | [6 empty] | E-ARK AIP |  |  | X | E-ARK DIP | [15 empty] | X
| Database Preservation Toolkit | Alfrsco Export Module | RODA-In | ESSArch Tool Producer (ETP) | ESSArch Tools Archive (ETA) | UAM | SIP creator (E-ARK Web) | SIP2AIP (E-ARK Web) | RODA Repository | ESSArch Preservation Platform | HDFS-Storage | ICA-AtoM Catalogue | OMT - Search and Dsiplay GUI | Order Submission Service | OMT - Order Management Tool | Lily - Ingest | ESSArch Preservation Platform | E-ARK Web (Search) | AIP2DIP (E-ARK Web) | DBPTK | IP Viewer | DB Viewer (Sofia) | ERMS Viewer (Alfresco) | Single file Viewr | QGIS | Geoserver | Peripleo | Oracle (OLAP Viwer)
[11 empty] | X |  |  |  |  | X |  | X | X |  |  |  |  | X
Use-case | Access databases via SOLR (no-sql)
Note | Access data from E-ARK web / HDFS storage and from locals system. SOLR is used for search the full text index generated of the ducuments.
Links | [Pilot Data Description] | [13 empty] | [Pilot Process Description]

## Pilot preparation
Pilot 7 | Pilot Preparation
Preparation status
Software component | Tool / Version number | Scenario | Process | Tool selected | Tool available for Pilot | Tool/Version installation | Tool configuration | Knowledge overtaken | Tool ready for Pilot
Preparation tasks related to the software components | from Software Component Matrix (for E-.ARK tools) | from Scenarios sheet | from Processes sheets | Yes /No / (issue) | Yes / (planned date of availability) | Installed / (issues) | No needed / Configured / (issues) | Yes / (issues) | Ready / (issues)
SIARD Suite (local?) |  | Scenario 3 | Access | yes | yes | Probable the install kit, published on 24.02.2016, contains a fixed versiom | A previouse version was already configured. | yes | Probably
DBPTK (RDBMS to SIARDX) (Database Preservation Toolkit) | 2.0.0-beta4.3 | Scenario 1, scenario 3, scenario 4 | Pre-ingest | yes | Yes | A previouse version is already installed and tested | A previouse version was already configured. | yes | Ready
RODA-In (SIP creation tool) | 2.0.0-alpha.7.3 | Scenario 1, Scenario 2 | Pre-ingest, Ingest |  |  |  |  | http://rodain.roda-community.org
Integrated prototype (SIP creation tool) |  | Scenario 1, Scenario 2 | Pre-ingest, Ingest?? | yes | No date available, under development. The Integrated prototype will be installed by 15. March according our plan | No, it is planned by 15.03,2016 | No configuration | Further knowladge transfer needed: training and user manual | Not ready, it must be installed
DBPTK (SIARDX to RDBMS) | 2.0.0-SNAPSHOT-232-3 | Scenario 3, Scenario 4 | Access | yes | yes
SIP2AIP (Integrated Prototype) |  | Scenario 1, scenario 3, scenario 4 | Ingest-Storage | yes | No date available, under development. The Integrated prototype will be installed by 15. March according our plan
Lily - Ingest (Integrated Prototype) |  | Scenario 3, Scenario 4 | Access | yes | No date available, under development. The Integrated prototype will be installed by 15. March according our plan
HDFS Storage (Integrated Prototype) |  | Scenario 3, Scenario 4 | Storage-Access | yes | No date available, under development. The Integrated prototype will be installed by 15. March according our plan
E-ARK WEB (Search) (Integrated Prototype) |  | Scenario 3, Scenario 4 | Access | yes | No date available, under development. The Integrated prototype will be installed by 15. March according our plan
AIP2DIP (Integrated prototype) |  | Scenario 1, Scenario2, Scenario 5 | Access | yes | No date available, under development. The Integrated prototype will be installed by 15. March according our plan | No, it is planned by 15.03,2016 | No configuration | Further knowladge transfer needed: training and user manual | Not ready, it must be installed
SDB/Preservica (local) |  | Scenario 1, scenario 2, scenario 4, Scenario 5 | Storage, access | yes | yes | installed | yes | yes | Ready
ELEV SIP Creator (local) |  | Scenario 1 | Ingest | yes | yes | installed | yes | yes | Ready
SIPKA (local) |  | Scenario 1 | Pre ingest | yes | yes | installed | yes | yes | Ready
Bürke (local) |  | Scenario 1 | Ingest | yes | yes | installed | yes, but it must be reconfigured to the new Oracle database installed on the Hadoop cluster | yes | Ready
Oracle RDBMS (local) |  | Scenario 1, scenario 3, scenario 4 | Pre ingest, ingest, access | yes | yes | installed | yes | yes | Ready
Oracle APEX (local) |  | Scenario 3 | Access | yes | yes, but the appropriate further development is part of the pilot | yes, but... | yes, but further configuration have to be done based on the developments | yes | Ready
Oracle BI (local) |  | Scenario 3 | Access | yes | yes, but the pilot needs a lot of developments within the software | yes, but... | yes, but further configuration have to be done based on the developments | yes | Ready
Oracle AWM (local) |  | Scenario 3 | Ingest, Access | yes | yes, but the pilot needs a lot of developments within the software | yes, but... | yes, but further configuration have to be done based on the developments | yes | Ready
SIARD-OLAP |  | Scenario 3 | Access | yes | No date available | No, it is being planned | No configuration | Further knowladge transfer needed | Not yet developed
Prepration status
Pilot dataset | Dataset # | Scenario | Data selected | Legal issues | Data available | Dataset ready for Pilot
Preparation tasks related to pilot data | from Pilot Data sheet | from Scenarios sheet | Yes / (issues) | None / (issue) | Yes / (planned date) / (issue) | Ready / (issue)
BÜR (Registry of the Hungarian Prosecution Offices) | Data set 1 | Scenario 1, Scenario 3, Scenario 4 | yes | Non | yes | yes
Meeting minutes of the AGITPROP Departement of the Hungarian Communist Party | Data set 2 | Scenario 2, Scenario 5 | yes | Non | yes | yes
…
Prepration status
Infrastructure | Scenario | Process | Element selected | Issues | Element ready for Pilot
Preparation tasks related to pilot infrastructure | from Scenarios sheet | from Processes sheets | Yes / (issues) | None / (issue) | Ready / (issue)
Application developed in Oracle APEX to present normalized and denormalized database | Scenario 3, Scenario 4 | Access | yes |  | Ready, but a lot of development is needed which is planned to be the part of the pilot
Denormalization of normalized relational databaase by Oracle BI | Scenario 1 | Pre-ingest, Ingest??? | yes |  | Ready, but a lot of development is needed which is planned to be the part of the pilot
Installation of Hadoop cluster | Scenario 4, Scenario 5 | Storage, Access | yes |  | By 29.02.2016
Generating OLAP Cubes | Scenario 3 | Pre-ingest, Ingest???, Access | yes |  | Ready, but a lot of development is needed which is planned to be the part of the pilot
Generatin an appropriate archival version of OLAP Cubes | Scenario 3 | Pre-ingest, Ingest???, Storage, Access | Not selected yet |  | Not ready, it is still under design
And much more
Note on A4: Please, list all relevant E-ARK and local software components. Example: - Data Preservation Toolkit - XIP Creator (local)
Note on C4: Please, select the scenario from the Pilot Scenarios sheet in which the tool is used
Note on D4: Please, select the process from the processes sheets in which the tool is used. Example: - Pre-Ingest - Access
Note on E4: Please, indicate whether the tool has benn selected (yes) or not yet (no), and any issues related tool selection (like: "Testing tool candidates")
Note on F4: Examples: - Yes - 01/04/2016 - No date available
Note on G4: Examples: - Installed - Planned at 01/04/2016 - Installation issues - No instal kit available
Note on H4: Examples: - No configuration needed - Configured - Configuration issues
Note on I4: Examples: - Yes - Training required - Further knowledge transfer needed - User Manual not available
Note on A26: Please list every data set from the Pilot Data sheet
Note on C26: Please, select the scenario from the Pilot Scenarios sheet in which the dataset is used
Note on D26: Please indicate wheather the data set has been selected yet
Note on E26: Example: - None - Under contracting with provider - Under negotiaitions with provider
Note on F26: Example: - Yes - 01/04/2016 - dataset not available by provider - access issues
Note on A33: Please list all infrastructure components that are relevant (and not obvious) for the pilot Like - special hardware elements - special database elements - special data viewers (not provided by E-ARK)
Note on B33: Please, select the scenario from the Pilot Scenarios sheet in which this infrastructure component is used
Note on C33: Please, select the process from the processes sheets in which this infrastructure component is used. Example: - Pre-Ingest - Access
Note on D33: Please indicate wheather the element has been selected yet

## Pre-Ingest
OAIS Process | Pre-Ingest
Main Process Stepps | Content definition Technical feasibility Legal issues etc. | Create/Review transfer agreement | Select data | Data Extraction | Manual compilation of non ERMS content | Metadata mapping | Create SIP | Post-packaging quality control | Submit SIP
Scenario 1 | SIP Creation and Ingest of old (not normalized) database in SIARD 2.0 format
Used E-ARK tool
Used local tools | Define restrictions | Paper-based TA | Local ERMS |  | Manual | SIPKA Actor adds metadata by a GUI interface of a standalone software application | SIPKA |  | DVD, Personal delivery
Perfomer (actor) | Data provider and Archives | Data provider and Archives | Data provider | Data provider | Data provider | Data provider | Data provider |  | Data provider
Prelemineries and Start condition
Input |  |  | Transfer Agreement | Selected Data | CSV files | CSV files in a predefined folder structure | Documentation (pdf, Excel files), primary data in CSM file, metadata in XML file
Output |  | Transfer Agreement | Data selected | CSV files | CSV files in a predefined folder structure | XML file | OAIS compliant Information Package
Scenario 2 | SIP Creation and Ingest of unstructured files
Used E-ARK tool | [5 empty] | RODA-In | RODA-In
Used local tools | [8 empty] | Total Commander (local tool)
Perfomer (actor) | Archives | - | Archives | Archives | Archives | Archives | Archives |  | Archives
Prelemineries and Start condition
Input |  |  | set of files |  |  | Metadata known by the archivists | set of files, metadata
Output |  |  | subset of a set of files |  |  | XML within a SIP under construction | E-ARK SIP

## Ingest
OAIS Process | Ingest
Main Process Stepps | Receive SIP | Security check | Integrity check | Sintax check | Format check | Review and Approve SIP | Modify SIP | Generate and Store AIP
Scenario 1 | SIP Creation and Ingest of old (not normalized) database in SIARD 2.0 format
Used E-ARK tool | [7 empty] | RODA-In, SIP2AIP
Used local tools | SIPKA | SIPKA | SIPKA | SIPKA | SIPKA | SIPKA | SIPKA | BÜRKE, SIARD Suite, Oracle, ELEV SIP Creator
Perfomer (actor) | Archives | Archives | Archives | Archives | Archives | Archives | Archives | Archives
Prelemineries and Start condition
Input | Specific SIP | Specific SIP | Specific SIP | Specific SIP | Specific SIP | Specific SIP | Approved SIP | Modified SIP
Output |  | check report | check report | check report | check report | Approved SIP | Modofied SIP | E-ARK SIP, SDB XIP
Scenario 2 | SIP Creation and Ingest of unstructured files
Used E-ARK tool | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator | RODA-In,earkweb SIP creator
Used local tools
Perfomer (actor) | Archives | Archives | Archives | Archives | Archives | Archives | Archives | Archives
Prelemineries and Start condition
Input | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | E-ARK SIP | Approved SIP | Modified SIP
Output |  | check report | check report | check report | check report | Approved SIP | Modofied SIP | E-ARK AIP

## Access
OAIS Process | Access
Main Process Stepps | Search & Select Records | Manage Order | Prepare DIP | Prepare DIP delivery | Deliver DIP | Access DIP | DIP Management
Scenario 3 | Extract SIARD Package from Preservica/E-ARK AIP
Used E-ARK tool | - | - | DPTK (SIARD2RDBMS)
Used local tools | SDB/Preservica (local tool) | ScopeArchive (local ) | Oracle RDBMS, APEX, Oracle BI |  | Oracle RDBMS, APEX | APEX, Oracle BI | Administration is ScopeArchive.
Perfomer (actor) | User, Archivist | Archivist | Archivist |  | Archivist | User, Archivist | Archivist
Preleminaries and Start condition
Input |  | user request | SDB DIP (OAIS Compliant) | RDBMS data | Oracle schema | RDBMS schema | Oracle RDBMS schema for access
Output |  | new/modified record | RDBMS shema (a subset and anonymized version of RDMS data in a different shema) |  | Oracle schema | RDBMS schema available through APEX application or/and Oracle BI | DIP created from Oracle RDBMS by DBPTK and RODA-In and stored in HDFS-Storage. Modified record in ScopeArchive
Scenario 4 | Search and present SIARD based information with E-ARK access tools
Used E-ARK tool | E-ARK Web (Search), Lily Ingest, HDFS Storage |  | DPTK (SIARD2RDBMS)
Used local tools |  | ScopeArchive | Oracle RDBMS, APEX, Oracle BI |  | Oracle RDBMS, APEX | APEX, Oracle BI | Administration is ScopeArchive.
Perfomer (actor) | User, Archivist | Archivist | Archivist |  | Archivist | User, Archivist | Archivist
Preleminaries and Start condition
Input | Search terms | user request | DIP exported by E-ARK Web from HDFS storage | RDBMS data | Oracle schema | RDBMS schema | Oracle RDBMS schema for access
Output | Result list | new/modified record | RDBMS shema (a subset and anonymized version of RDMS data in a different shema) |  | Oracle schema | RDBMS schema available through APEX application or/and Oracle BI | DIP created from Oracle RDBMS by DBPTK and RODA-In and stored in HDFS-Storage. Modified record in ScopeArchive
Scenario 5 | Access information from unstructured files
Used E-ARK tool | E-ARK Web (Search), Lily, HDFS-Storage |  | AIP2DIP
Used local tools |  | ScopeArchive | image manipulation software (if needed) |  | Internet, LAN, File system | Oracle BI, APEX | Administration is ScopeArchive.
Perfomer (actor) | User, Archivist | Archivist | Archivist |  | Archivist | User, Archivist | Archivist
Preleminaries and Start condition
Input | Search terms | user request | DIP exported by E-ARK Web from HDFS storage |  | DIP | DIP | DIP
Output | Result list | new/modified record | DIP (with a subset of the exported DIP from the HDFS) |  | DIP | DIP | DIP stored in HDFS-Storage. Modified record in ScopeArchive

## Backup Lists
OAIS Processes
Pre-Ingest
Ingest
Preservation
Data Management
Access
IP Formats
E-ARK SIP format
non-E-ARK SIP format
E-ARK AIP format
non-E-ARK AIP format
E-ARK DIP format
non-E-ARK DIP format
Pre-Ingest Use-cases
Extract and Ingest relational database based on SIARD 2.0
Extract and Ingest ERMS records based on MoReq2010
Extract and Ingest computer files from simple file-system - GML
Extract and Ingest computer files from simple file-system - Other (please specify)
Other (please specify in the Note field)
Native metadata format of producer system
MoReq 2
MoReq 2010
ApeEAD
EAD 1
EAD 2
EAD 3
Other (Please specify in the Note field)
Pre-Ingest Process Steps
Content definition, technical feasibility, legal issues, etc.
Create/review transfer agreement
Select data
Manual compilation of non ERMS content
Data extraction
Metadata mapping
Create SIP
Post-packaging control
Submit SIP
Receive SIP
Security check
Formal validation
Content review and approval
Modify SIP
Generate and store AIP
Search & Order Management
DIP Preparation
DIP Delivery
DIP Management
Other (please specifiy)
Pre-Ingest / Ingest Tools
Alfresco Export Module for MoReq2010-based extraction
ESSArch Tools for SIP preparation and creation
Database Preservation Toolkit for creating SIARD2.0 from relational
SIP-AIP Module
Other non-E-ARK tool (please specify)
Access Tools
Search Module
Order Module
DIP Management Module
AIP-DIP Module
Presentation Module
Other non-E-ARK tool (please specify)
Access Use-cases
Access databases via Sofia (sql)
Access databases via SOLR (no-sql)
Access single ERMS records via alfresco cms
Access geodata via qgis
Access data with OLAP via oracle
Other (please specify content type and presentation tool)